STATEMENT OF WORK

Local Service Delivery & Booking Platform — MVP

Prepared for: [Client Name]

Prepared by: Harsh Mishra, Project Manager

Date: 2 September 2026

Reference: Business Requirements Document (BRD) v1.0, 23 August 2026 — Pratima Vanakhade

Version: 1.0, Draft for review

This SOW sets out what we're building, for how much, and by when — a scoped-down MVP of the platform described in the BRD, sized to fit the current budget and a four-week delivery window. It's meant to be read alongside the BRD, not in place of it: anything not explicitly listed here as in-scope should be assumed out of scope for this round.

1. What this document covers

This Statement of Work lays out the scope, deliverables, timeline, team, and cost for building an MVP version of the Local Service Delivery & Booking Platform described in the BRD.

Worth being upfront about: the BRD describes a much bigger platform — AI recommendations, complaint management, social media integration, loyalty and wallet, a full Azure setup. None of that is in this round. At ₹1,00,000 and four weeks, this SOW covers a stripped-back MVP that proves out the core booking experience. The rest would be a separate, larger engagement once this version is validated. Section 4.2 lists exactly what's excluded.

2. Background

The BRD outlines a platform connecting customers with verified local service providers — electricians, plumbers, tutors, cleaners, and similar — with booking, CRM, loyalty, wallet, and AI-driven insights built on top. This SOW is the first step toward that: a working booking flow customers and providers can actually use, built fast and cheap enough to validate the idea before investing further.

3. Why we're building this

The bigger goal is a trusted platform where customers can find and book local services easily, providers get a real channel for bookings and payments, and the business gets a single system to manage everything with proper data protection built in. This MVP is about proving the core loop works — search, book, confirm — before spending the time and budget on the rest of it.

4. Scope of work

4.1 What's included

| Module | What it does |
| --- | --- |
| Customer sign-up & login | Register with email or mobile, log in with OTP. |
| Basic service search | Browse and search services by category or keyword. |
| Provider listings | Providers are added manually by the team, with pricing and availability shown to customers. |
| Booking flow | Search, pick a provider, pick a service, confirm — booking is created and tracked through Requested, Confirmed, Completed, or Cancelled. |
| Internal admin view | A simple screen for the team to see current bookings and providers. |
| Hosting | Deployed on a single hosted environment, enough to demo and validate the MVP. |

4.2 What's not included

Everything below is in the BRD but not this round — either because of budget, timeline, or because it depends on things (like a licensed payment partner) that haven't been set up yet:

- AI-based recommendations, insights, or complaint classification

- Digital wallet and loyalty points

- Social media complaint handling and a dedicated complaints dashboard

- Formal KYC/verification for providers, and encrypted storage of sensitive provider data

- MFA, full role-based access control, data masking, and audit logging as described in the BRD

- A full management dashboard with KPIs and analytics

- Data export tooling for customer service staff

- The full Azure architecture (API Management, Key Vault, Redis, Service Bus, AI Foundry, WAF, etc.)

- Any real payment processing or integration with a licensed wallet provider

4.3 A note on security

The full security setup in the BRD — field-level encryption, masking, MFA, audit logging — isn't part of this MVP. We'll use standard HTTPS and basic authentication, which is fine for testing the concept but not for handling real financial data or government IDs. Please don't put either into this build.

5. Deliverables

Each deliverable below maps to a scope item above and lands within the 4-week window.

| ID | Deliverable | What it is | Target |
| --- | --- | --- | --- |
| D1 | MVP outline | A short technical plan and data model covering just the modules below. | Week 1 |
| D2 | Sign-up & login | Registration and OTP login, deployed to staging. | Week 1–2 |
| D3 | Search & listings | Category/keyword search and manually-added provider listings. | Week 2 |
| D4 | Booking flow | Search through to confirmed booking, with status tracking. | Week 2–3 |
| D5 | Admin view | Internal screen to see bookings and providers. | Week 3 |
| D6 | Testing & fixes | Client review and fixes for anything blocking launch. | Week 3–4 |
| D7 | Launch | Deployed and handed over. | Week 4 |

6. How we'll get there

Four weeks doesn't leave room for a long planning phase, so this runs as short sprints with Yash keeping things moving:

- Week 1 — nail down the data model and screens, get hosting set up, build login.

- Week 2 — search and provider listings.

- Week 3 — booking flow and the admin view; testing starts.

- Week 4 — fix what testing turns up, deploy, hand over.

7. Team

| Name | Role | What they own |
| --- | --- | --- |
| Harsh Mishra | Project Manager | Delivery, client communication, keeping scope and timeline on track. |
| Armaan Mulani | Tech Lead & Solution Architect | Architecture, technical decisions, code quality. |
| Yash Khapre | Scrum Master | Sprint planning, clearing blockers. |
| Pratima Vanakhade | Business Analyst | Requirements traceability back to the BRD, UAT support. |

Any additional developers or QA needed to hit the timeline will be pulled in by the team as required — they're not named individually here.

8. Who's responsible for what

8.1 Client

- Harsh Mishra acts as Business/Product Owner — approves requirements and signs off deliverables.

- Share any existing brand assets or content needed for the MVP screens.

- Turn around deliverable reviews within 2 business days — with only 4 weeks, delays here eat directly into the schedule.

- Confirm hosting/domain details ahead of deployment.

- Understand and accept that this MVP runs on a lighter security setup than the full platform (more on this below).

8.2 Delivery team

- Build strictly to the scope in this document — nothing from the BRD beyond what's listed here.

- Harsh Mishra (PM) — single point of contact, keeps the plan and issue list up to date.

- Armaan Mulani (Tech Lead) — owns technical decisions and the MVP's architecture.

- Yash Khapre (Scrum Master) — runs the sprints and clears blockers.

- Pratima Vanakhade (BA) — keeps the build honest against the BRD and supports testing.

- Flag anything that risks scope, schedule, or budget as soon as it comes up, rather than after the fact.

9. Timeline

Four weeks from kickoff. Rough milestones:

| Milestone | What's done | When |
| --- | --- | --- |
| M1 | SOW signed, kickoff | Week 0 |
| M2 | MVP outline finalized | Week 1 |
| M3 | Login, search, and listings built | Week 1–2 |
| M4 | Booking flow and admin view built | Week 2–3 |
| M5 | Testing and fixes | Week 3–4 |
| M6 | Live | Week 4 |

Given how tight the schedule is, we're asking for a 2-business-day turnaround on reviews — anything slower starts pushing the launch date.

10. Baseline technical standards

The full non-functional requirements in the BRD are out of scope for this phase (see 4.3). What we will do:

| Area | What applies here |
| --- | --- |
| Security | HTTPS everywhere; OTP and passwords handled securely. |
| Access | Basic login required for booking and admin actions — not full role-based access. |
| App security | Standard input validation and protection against common issues like XSS and SQL injection. |
| Uptime | Best-effort — no formal SLA at this stage. |
| Monitoring | Basic logging for debugging; nothing centralized yet. |

11. When we call it done

The MVP is accepted once:

- A customer can register or log in with OTP.

- A customer can search services by category or keyword and see provider listings with price and availability.

- A customer can complete a booking end-to-end — provider, service, confirm.

- Booking status moves correctly through Requested, Confirmed, Completed, and Cancelled.

- The admin view correctly shows current bookings and providers.

- The app is live and reachable on the hosted environment.

Harsh, as Product Owner, will give written sign-off (email is fine) once these are confirmed.

12. Changes to scope

If something comes up that adds to, removes, or changes what's listed in Section 4, it goes through a quick change request — what's changing, what it does to timeline and cost — and both sides sign off before work starts on it.

13. Assumptions

- Providers added during the MVP are vetted manually by the team, not through a formal KYC process.

- No real payments are collected in-app during this phase.

- No real financial or government ID data will be entered into the system.

- Harsh will keep to the 2-day review turnaround given how tight the schedule is.

- The full BRD scope is a separate engagement, to be scoped once this MVP is live and validated.

14. Constraints

- ₹1,00,000 and four weeks is what defines the scope in Section 4 — nothing more fits in this round.

- No sensitive financial or ID data should touch this build, given the lighter security setup.

- Anything from the excluded list needs its own budget, timeline, and sign-off before it's added.

15. Risks

| Risk | Impact | What we'll do about it |
| --- | --- | --- |
| No formal provider vetting in this MVP | Medium | Team manually checks providers added during the build; proper KYC comes later. |
| Client expects full BRD functionality for this budget | High | This document spells out what's excluded (Section 4.2) — worth confirming everyone's aligned before kickoff. |
| Four weeks is tight — little room for delay | Medium | Hold to the 2-day review turnaround and flag slippage early rather than late. |
| Scope creep during the build | Medium | New requests get logged as change requests, not folded in quietly. |
| Real financial or ID data ending up in an MVP that isn't built to protect it | High | No such data should be entered into the system during this phase; move to the full security build before handling anything sensitive. |

16. Cost

| Item | Details |
| --- | --- |
| Type | Fixed price |
| Total | ₹1,00,000, covering the scope in Section 4.1 only |
| Payment | Suggested: 40% at kickoff, 30% at Milestone M4, 30% at launch — to confirm |
| Invoicing | To confirm |
| Hosting costs | Billed separately if they go beyond free-tier limits |
| Post-launch support | 1–2 weeks of bug fixes suggested — to confirm |

This budget covers Section 4.1 only. Anything from the excluded list needs its own budget and its own SOW.

17. Confidentiality & ownership

- Anything shared during this project — customer data, business details — stays within the team.

- As noted earlier, no real financial or ID data belongs in this build.

- Once payment is complete, the code and documentation produced here belong to the client, unless agreed otherwise in writing.

18. Staying in touch

- Harsh is the point of contact for anything project-related.

- Given the four-week window, quick check-ins every 2–3 days work better than a weekly cadence.

- Technical questions can go straight to Armaan.

19. Sign-off

Signing below means agreeing to the scope, deliverables, timeline, and cost in this document.

| Name | Role | Organization | Signature | Date |
| --- | --- | --- | --- | --- |
| [Client Name] | Business / Product Owner | Client |  |  |
| Harsh Mishra | Project Manager | Delivery Team |  |  |
| Armaan Mulani | Tech Lead & Solution Architect | Delivery Team |  |  |